## Functions
Screen/Function | Type | Table_name 1 | Table_name 2 | Table_name 3 | Table_name 4 | Business Process | Use Cases | In Charge | Iteration | SRS | SDS | Status | Notes / Updates
Branch Management (CRUD) | Screen | cinemas |  |  |  | Cinema Branch Management | Manage Cinema Branches: As an Admin, I want to view, add, edit, or deactivate cinema branches across the chain. | Dũng | Iteration 1 | M-04.1 | BranchAdminServlet | In Progress
Screening Room Management (CRUD) | Screen | screening_rooms | cinemas |  |  | Showtime & Room Management | Manage Screening Rooms: As an Admin, I want to view, add, edit rooms and room formats (2D, 3D, IMAX) by branch. | Dũng | Iteration 1 | M-04.2 | RoomAdminServlet | In Progress
Seat Layout Designer | Screen | seats | seat_types | screening_rooms |  | Showtime & Room Management | Configure Seat Layout: As an Admin, I want to design seat matrix (A-Z x 1-N) and seat types (Standard, VIP, Couple) for each hall. | Dũng | Iteration 1 | M-04.3 | SeatGridServlet | In Progress | Đẩy lên Iter 1 để làm nền cấu trúc ghế cho Linh ở Iter 2
System Settings | Screen | system_settings |  |  |  | System Administration | Manage System Parameters: As an Admin, I want to configure global params (holding duration 5m, cleaning buffer 15m). | Dũng | Iteration 1 | M-11 | SettingAdminServlet | In Progress
Admin Dashboard | Screen | cinemas | bookings | payments |  | Dashboard & Reporting | View System Overview: As an Admin, I want a high-level operational overview across all branches. | Dũng | Iteration 2 | M-11 | AdminDashboardServlet | To Do
Seat Maintenance Toggle | Screen | seats | maintenance_schedules |  |  | Showtime & Room Management | Toggle Seat Maintenance: As an Admin/Manager, I want to mark broken seats under maintenance to prevent sales. | Dũng | Iteration 2 | M-04.3 | SeatGridServlet | To Do
Branch Occupancy Report | Screen | showtimes | tickets | screening_rooms |  | Dashboard & Reporting | Monitor Hall Occupancy: As a Cinema Manager/Admin, I want to track seat occupancy rates across halls and time slots. | Dũng | Iteration 2 | M-10.3 | ReportAdminServlet | To Do
Revenue & Sales Reports | Screen | bookings | tickets | order_items | payments | Dashboard & Reporting | Generate Revenue Reports: As an Admin, I want to view revenue reports by date, movie, branch and export Excel/PDF. | Dũng | Iteration 3 | M-10.1 | ReportAdminServlet | To Do
Enterprise BI & Comparison Reports | Screen | cinemas | bookings | payments | showtimes | Dashboard & Reporting | Compare Branch Performance: As an Admin, I want to view chain-wide comparison reports, performance metrics, and export data. | Dũng | Iteration 3 | M-10.2 | ReportAdminServlet | To Do
Home Page & Browsing | Screen | movies | genres | movie_genres |  | Home & Movie Browsing | View Now Showing & Coming Soon: As a guest, I want to browse movies currently showing and coming soon on homepage. | Thịnh | Iteration 1 | M-01.1 | MovieServlet | In Progress
Movie Detail & Trailer | Screen | movies | genres |  |  | Home & Movie Browsing | View Movie Details: As a user, I want to view trailer, duration, age rating (T13/T16/T18), and synopsis of a movie. | Thịnh | Iteration 1 | M-01.1 | MovieServlet | In Progress
Movie Search & Filter | Screen | movies | genres |  |  | Home & Movie Browsing | Search & Filter Movies: As a user, I want to search movies by title and filter by genre and age rating. | Thịnh | Iteration 1 | M-01.1 | MovieServlet | In Progress
Admin Master Movie Catalog (CRUD) | Screen | movies | movie_genres | genres |  | Movie Management | Manage Master Catalog: As an Admin, I want to add, edit, or archive movies in the master catalog with metadata and posters. | Thịnh | Iteration 1 | M-02.1 | MovieAdminServlet | In Progress
Showtime Schedule View | Screen | showtimes | movies | screening_rooms |  | Showtime & Room Management | View Showtimes: As a customer, I want to view showtime schedules by movie, date, and cinema branch. | Thịnh | Iteration 2 | M-01.1 | ShowtimeManagementServlet | To Do
Showtime Creation & Scheduling | Screen | showtimes | screening_rooms | system_settings |  | Showtime & Room Management | Schedule Branch Showtimes: As a Cinema Manager, I want to create showtimes with automatic 15-minute cleaning buffer check. | Thịnh | Iteration 2 | M-03.1 | ShowtimeManagementServlet | To Do
Dynamic Pricing Configuration | Screen | ticket_pricings | seat_types |  |  | Showtime & Room Management | Configure Pricing Template: As an Admin/Manager, I want to set base prices by format (2D/3D), time slot, and concession customer types (Student/Senior). | Thịnh | Iteration 2 | M-03.2 | PricingAdminServlet | To Do
Customer Movie Review | Screen | reviews | movies | users |  | reviews | Rate & Review Movies: As a Customer, I want to rate 1-5 stars and write a review after watching a movie. | Thịnh | Iteration 3 | M-02.2 | ReviewServlet | To Do
Admin Review Moderation | Screen | reviews | users |  |  | reviews | Moderate User Reviews: As an Admin, I want to approve, hide, or delete inappropriate reviews. | Thịnh | Iteration 3 | M-02.2 | ReviewAdminServlet | To Do
Seat Selection UI & DTO Engine | Screen | seats | seat_types | screening_rooms |  | Booking System | Select Seats: As a Customer, I want to choose available seats from the visual hall map with seat type pricing and DTO layout model. | Linh | Iteration 1 | M-05.1 | BookingFlowServlet | In Progress | Khởi động nền tảng cấu trúc dữ liệu ghế chuẩn bị cho engine giữ chỗ
Pessimistic Seat Holding Logic | Service | seat_holdings | seats |  |  | Booking System | Temporarily Lock Seats: As the System, I want to lock selected seats for 5 minutes (Pessimistic Lock) to prevent double booking. | Linh | Iteration 1 | M-05.3 | BookingEngineServiceImpl | In Progress | Thiết lập cơ chế khóa giữ ghế 5 phút chống đặt trùng
Auto-Release Expired Holds | Service | seat_holdings | seats |  |  | Booking System | Release Expired Seats: As the System, I want to release holds older than 5 minutes automatically via background scheduler. | Linh | Iteration 2 | M-05.3 | BookingEngineServiceImpl | To Do
Online Booking Checkout | Screen | bookings | tickets | order_items | payments | Booking System | Confirm Booking: As a Customer, I want to review booking summary, ticket prices, and F&B combos before payment. | Linh | Iteration 2 | M-05.1 | BookingFlowServlet | To Do
VNPay Payment Gateway Integration | External API | payments | bookings |  |  | Payment | Pay via VNPay: As a Customer, I want to pay online securely via VNPay gateway with IPN webhook confirmation. | Linh | Iteration 2 | M-06.1 | PaymentServlet | To Do
E-Ticket QR Code Generation | Service | tickets | bookings |  |  | Ticket & Entry | Generate E-Ticket QR: As the System, I want to generate digital tickets with cryptographic HMAC-SHA256 QR codes after payment. | Linh | Iteration 2 | M-07.1 | CustomerBookingServlet | To Do
Customer Booking History | Screen | bookings | tickets | showtimes |  | Booking System | View Booking History: As a Customer, I want to view my past and upcoming booking details, tickets, and entry QR codes. | Linh | Iteration 3 | M-05.4 | CustomerBookingServlet | To Do
Cancel Booking (Conditional) | Screen | bookings | tickets | payments | seats | Booking System | Cancel Booking (Conditional): As a Customer, I want to cancel paid booking at least 2 hours before showtime for automated refund and seat release. | Linh | Iteration 3 | M-05.4 | CustomerBookingServlet | To Do
Customer Payment Tracking & E-Invoice | Screen | payments | bookings |  |  | Payment | Track Payment & Invoices: As a Customer, I want to view payment details, track status, and download electronic receipts. | Linh | Iteration 3 | M-06.3 | PaymentServlet | To Do
User Login | Screen | users | roles |  |  | Authentication & Account | Login System: As a user, I want to log in with email and password (BCrypt hashed) to access authorized features. | Cường | Iteration 1 | M-01.2 | AuthServlet | In Progress
User Register | Screen | users | roles |  |  | Authentication & Account | Register Account: As a guest, I want to register an account with OTP email verification so that I can become a member. | Cường | Iteration 1 | M-01.1 | AuthServlet | In Progress
User Logout | Screen | users |  |  |  | Authentication & Account | User Logout: As an authenticated user, I want to log out and invalidate my session securely. | Cường | Iteration 1 | M-01.2 | AuthServlet | In Progress
Forgot / Reset Password | Screen | users |  |  |  | Authentication & Account | Reset Password: As a user, I want to reset my password via a 15-minute token/OTP sent to my email. | Cường | Iteration 2 | M-01.2 | AuthServlet | To Do
Customer Profile & Change Password | Screen | users |  |  |  | Authentication & Account | Manage Profile & Password: As a Customer, I want to view/edit my profile info and update account password. | Cường | Iteration 2 | M-01.3 | ProfileServlet | To Do
Admin User Management | Screen | users | roles | cinemas |  | Authentication & Account | Manage Users: As an Admin, I want to view, search, filter, and activate/deactivate accounts across the system. | Cường | Iteration 2 | M-01.4 | UserAdminServlet | To Do
Admin Role & Branch Assignment | Screen | users | roles | cinemas |  | Authentication & Account | Assign Role & Branch: As an Admin, I want to assign/transfer staff and managers to cinema branches. | Cường | Iteration 3 | M-01.4 | UserAdminServlet | To Do
Booking & Ticket Notification Service | Service | bookings | tickets | users |  | Notification Management | Send Booking Notification: As the System, I want to send confirmation email with QR e-ticket attachment upon successful payment. | Cường | Iteration 3 | M-09.1 | EmailServiceImpl | To Do | Đảm nhận module M-09 dựa trên nền tảng OTP email từ Iteration 1
Showtime Alert & Refund Notification | Service | showtimes | bookings | users |  | Notification Management | Send Showtime & Refund Alerts: As the System, I want to email customers showtime reminders or cancellation/refund notices. | Cường | Iteration 3 | M-09.1, M-09.2 | EmailServiceImpl | To Do | Gửi thông báo hoàn hủy và nhắc giờ chiếu trước suất chiếu
Concession Public Menu | Screen | fnb_items | fnb_categories |  |  | Concessions / Snacks | Browse F&B Menu: As a customer or staff, I want to view available snacks, popcorn, drinks, and combos with prices. | Tuyển | Iteration 1 | M-08.2 | PosCounterServlet | In Progress
Admin F&B Catalog Management | Screen | fnb_items | fnb_categories |  |  | Concessions / Snacks | Manage F&B Catalog: As an Admin, I want to add, edit, or disable snacks, categories, and combos. | Tuyển | Iteration 1 | M-08.1 | ConcessionAdminServlet | In Progress
Branch F&B Inventory Management | Screen | cinema_inventories | fnb_items |  |  | Concessions / Snacks | Manage Branch Stock: As a Cinema Manager/System, I want to update stock quantity, auto-deduct upon sales, and auto-flag Out-of-Stock. | Tuyển | Iteration 2 | M-08.1 | ConcessionAdminServlet | To Do | Kiểm kê tồn kho chi nhánh, kích hoạt cơ chế Out-of-Stock
POS Counter Sales | Screen | fnb_items | showtimes | bookings | tickets | Staff Operations | Sell Tickets & F&B at Counter: As Cinema Staff, I want a fast POS interface to book tickets, select concession ticket types (Standard/Student/Senior) upon ID check, and add snacks. | Tuyển | Iteration 2 | M-05.2 | PosCounterServlet | To Do
POS Counter Payment & Physical Receipt | Service | bookings | tickets | payments |  | Payment | Process Counter Payment: As Cinema Staff, I want to collect cash or VNPay QR recorded under staff_id and print receipt/tickets immediately. | Tuyển | Iteration 2 | M-06.2 | PosOrderServiceImpl | To Do
QR Ticket Scanner & Check-in | Screen | tickets | ticket_checkin_logs |  |  | Staff Operations | Validate QR Ticket: As Cinema Staff, I want to scan customer QR ticket via webcam/scanner to verify validity, hall, showtime, and mark ticket as USED. | Tuyển | Iteration 3 | M-07.2 | ScannerServlet | To Do
Gate Age & Concession Eligibility Verification | Service | tickets | movies | ticket_checkin_logs |  | Staff Operations | Gate Verification: As Cinema Staff, I want to verify customer age against movie rating (T13/T16/T18) and check student ID for concession tickets. | Tuyển | Iteration 3 | M-07.2 | CheckinServiceImpl | To Do
Ticket Reissue / Cancel & Reprint | Screen | tickets | bookings |  |  | Staff Operations | Reissue, Cancel or Reprint Ticket: As Cinema Staff, I want to search tickets by phone/code, reprint lost tickets, or process authorized ticket cancellation and rollback. | Tuyển | Iteration 3 | M-07.1 | TicketReprintServlet | To Do

## Use Case
Use Case | Entity1 (CRUD) | Entity2 (CRUD) | Primary Actor | Secondary Actor | Description
View Home Page & Movie Catalog | Movie (Read) | Genre (Read) | Guest | None | As a guest, I want to view now showing and coming soon movies on the home page so that I can discover movies.
View Movie Details & Trailer | Movie (Read) |  | Guest | None | As a guest, I want to view movie synopsis, duration, age rating and watch trailer so that I can choose what to watch.
Search & Filter Movies | Movie (Read) | Genre (Read) | Guest | None | As a guest, I want to search movies by title and filter by genre so that I can quickly find my preferred movie.
View Cinema Branches | Cinema (Read) |  | Guest | None | As a guest, I want to view the list of cinema locations and hotline so that I can choose a cinema near me.
View Showtime Schedules | Showtime (Read) | Movie (Read) | Guest | None | As a guest, I want to check movie screening schedules and hall types across dates and branches.
Register Account | User (Create) |  | Guest | Email Service | As a guest, I want to register an account with email verification so that I can become a registered customer.
User Login | User (Read) |  | Customer | None | As a registered customer, I want to log in with email and password so that I can access personalized features.
User Logout | User (Read) |  | Customer | None | As a logged-in user, I want to log out to terminate my active session.
Reset Forgotten Password | User (Update) |  | Customer | Email Service | As a customer, I want to receive a 15-minute password reset token via email so that I can recover my account.
Manage Customer Profile | User (Read, Update) |  | Customer | None | As a customer, I want to view and update my phone number, full name, and avatar.
Change Password | User (Update) |  | Customer | None | As a customer, I want to update my account password to maintain security.
Select Seats & Hold 5 Minutes | SeatHolding (Create) | Seat (Read) | Customer | System Lock | As a customer, I want to select seats on the visual room map and hold them for 5 minutes during checkout.
Select F&B Combos | FnBItem (Read) | OrderItem (Create) | Customer | None | As a customer, I want to add popcorn and beverage combos to my booking order.
Pay Booking via VNPay | Payment (Create) | Booking (Update) | Customer | VNPay Gateway | As a customer, I want to complete payment online via VNPay gateway to confirm ticket purchase.
View Booking History & E-Ticket | Booking (Read) | Ticket (Read) | Customer | None | As a customer, I want to access my booking history and view digital QR tickets for cinema entry.
Cancel Booking (Conditional) | Booking (Update) | Ticket (Update) | Customer | System / VNPay Refund | As a customer, I want to cancel my paid booking at least X hours prior to screening to receive an automated refund and release reserved seats.
Submit Movie Rating & Review | Review (Create, Update) | Movie (Read) | Customer | None | As a customer, I want to rate 1-5 stars and write a movie review after watching.
Sell Tickets at Counter | Booking (Create) | Ticket (Create) | Cinema Staff | None | As Cinema Staff, I want to select showtimes, seats, select concession ticket types (Standard/Student/Senior) upon ID verification, and create booking orders at counter.
Order F&B at Counter | OrderItem (Create) | FnBItem (Read) | Cinema Staff | None | As Cinema Staff, I want to browse menu with real-time stock check, and add food & drink items to customer orders at the POS counter.
Process Counter Payment | Payment (Create) | Booking (Update) | Cinema Staff | None | As Cinema Staff, I want to collect cash or VNPay payment recorded with staff_id and print receipt at counter.
Print Ticket | Ticket (Read) |  | Cinema Staff | Thermal Printer | As Cinema Staff, I want to print physical ticket paper with barcodes for counter customers.
Validate QR Ticket | Ticket (Read, Update) | TicketCheckinLog (Create) | Cinema Staff | QR Camera Scanner | As Cinema Staff, I want to scan QR code on customer e-tickets to validate entry, verify showtime & hall, and prevent duplicate entry.
Verify Age & Concession Eligibility | Movie (Read) | Ticket (Read) | Cinema Staff | None | As Cinema Staff, I want to check customer identity card against movie age restriction ratings (T13/T16/T18) and student card for concession tickets.
Reissue / Cancel Ticket | Ticket (Update) | Booking (Update) | Cinema Staff | None | As Cinema Staff, I want to cancel tickets with authorized rollback or reissue tickets for customers.
Look Up & Reprint Ticket | Ticket (Read) | Booking (Read) | Cinema Staff | None | As Cinema Staff, I want to look up tickets by booking code or customer phone number to reissue lost tickets.
Schedule Branch Showtimes | Showtime (CRUD) | ScreeningRoom (Read) | Cinema Manager | System Buffer | As Cinema Manager, I want to schedule showtimes with automatic 15-minute room cleaning buffer validation.
Configure Branch Pricing & Rates | TicketPricing (CRUD) |  | Cinema Manager | None | As Cinema Manager, I want to configure and override ticket pricing rules for specific local branch requirements.
Monitor Hall Occupancy | Showtime (Read) | Ticket (Read) | Cinema Manager | None | As Cinema Manager, I want to view real-time seat occupancy and booking status across halls.
Manage Branch F&B Stock | CinemaInventory (CRUD) | FnBItem (Read) | Cinema Manager | None | As Cinema Manager, I want to inspect and update concession inventory levels per branch with automated out-of-stock guards.
Toggle Seat Maintenance Status | Seat (Update) | MaintenanceSchedule (Create) | Cinema Manager | None | As Cinema Manager, I want to set damaged seats under maintenance to prevent customer booking.
View Branch Revenue & Sales Reports | Booking (Read) | Payment (Read) | Cinema Manager | None | As Cinema Manager, I want to inspect sales and revenue reports for my branch.
Manage User, Staff & Manager Accounts | User (CRUD) | Role (Read) | Administrator | None | As an Administrator, I want to create, update, deactivate staff accounts and assign them to branches.
Manage Master Movie Catalog | Movie (CRUD) | Genre (CRUD) | Administrator | None | As an Administrator, I want to add, edit, or archive movies and configure genres and age ratings.
Manage Cinema Branches & Halls | Cinema (CRUD) | ScreeningRoom (CRUD) | Administrator | None | As an Administrator, I want to add, edit, or archive cinema branches, screening halls, and configure hall formats.
Configure Seat Grid Designer | Seat (CRUD) | SeatType (CRUD) | Administrator | None | As an Administrator, I want to configure the physical seat matrix and layout per hall.
Configure Default Pricing Template | TicketPricing (CRUD) |  | Administrator | None | As an Administrator, I want to configure chain-wide default pricing by hall format, seat type, time slot, and concession customer types.
Manage Global F&B Catalog | FnBItem (CRUD) | FnBCategory (CRUD) | Administrator | None | As an Administrator, I want to manage master food and drink items, categories, and standard retail prices.
Moderate User Reviews | Review (CRUD) |  | Administrator | None | As an Administrator, I want to approve or hide customer reviews containing inappropriate content.
Generate Enterprise BI Reports | Booking (Read) | Payment (Read) | Administrator | None | As an Administrator, I want to view chain-wide financial performance, branch comparisons, and export Excel.
System Dashboard & Global Parameters | SystemSetting (CRUD) |  | Administrator | None | As an Administrator, I want to configure system parameters like hold duration and point accumulation ratio.